## FS Queries
Sr No | Document | Page / Section | Reference | Inquiry | Category | Requestor | Status | Comments / Response | Responder
1 | Nested Product Governance | Pg 8/2.1.2.2. Removing Product Revisions From Parent | 3) If the sub-product being removed is part of product configuration hierarchy, the product configuration parent must be adjusted. | What does 'adjusted' refer to here? Eg : PC Turbine 9-------Turbine9 ¦_PC Turbine------¦_Turbine ¦_PC Sub Prod1--¦_Sub Prod1 ¦_PC Sub Prod2--¦_Sub Prod2 If Configuration feature of Sub Prod1 is rolled up to Top product Turbine9 and Turbine 9 uses the rolled up feature/options for PC Turbine9 generation then PC Turbine9 feature/options should be updated/adjusted by deselecting feature options of Sub Prod1. Please confirm. |  |  | Closed | No relation with roll up function and sub product removal
2 | Nested Product Governance | Pg 11/2.1.2.6 Product Change Management | 3)Sub Products must be of a HIGHER or EQUAL revision as that of Parent. (Bottom Up Release) | What is the business application of this? Eg : If we have a 20-level structure. To revise the parent product, why should we revise all the 19 child products under it? |  |  | Closed | It’s a higher state not a revision.Sub Product must be in higher state to parent to support bottom-up approach.
3 | Nested Product Governance | Pg 12/2.1.2.6 Product Change Management | When an Engineering Change is Released with Affected Items | How will the notifications be sent? Will it be an Email or an Iconmail? |  |  | Closed | Icon mail
4 | Nested Product Governance | Pg 25 / Section 4-Acceptance Tests | Test Cases 4 and 5 ---> Expected Result. The 2nd point on the Expected Results says, "The Example will never several sub levels" | What is this referring to? Please clarify. |  |  | Closed | The example will have several sub levels
5 | Nested Product Governance | Pg 27 / Section 4-Acceptance Tests | Test Case 12 : Expected Result says : "Revising Product Revision  If a Product is revisable (Release)  From Category Menu for a Product, going to Revisions will show all revisions.  Executing Create New will create another revision.  Revision should be created.  Configuration Features, Inclusion Rules etc should be copied over to new revision, except for Design Variants and Product Configurations.  There is no float on release. | What does the statement, " There is no float on release" indicate here? Does it mean Configuration Features, Inclusion Rules etc should be replicated from earlier revision to new revision when new revision is created (before release). So, what else comes on release state of new revision for replicating the relationships? |  |  | Closed | Clear
6 | Nested Product Governance | General | Prevent Circular Reference for Nested Products 1.P1-->P1(not possible in EBOM) 2.P1--->P2--->P1(not possible in EBOM) 3.P1---->P2,P2(possible in EBOM because of find number) 4.P1---->P2---->P3---->P1(in EBOM not possible) | Please confirm the behavior for3rd & 4th case |  |  | Closed | 3rd & 4th case would not be supported.
7 | Nested Product Governance | Page22 | Refer Replace with higher revision section table: Rules to enforce -Disconnect existing item. -Connect current item. -parent product should not be in released/obsolete state -Parent Product should be equal or lower state as to replaced product. -product configuration in parent product configuration hierarchy should not be in active state -Perform refreshing of Structure view | Should Parent Product be in Preliminary state only as per Add Existing and delete Sub-product operations (Page 17 &21 description). Else it will contractict the behavior for Add existing and Replace with higher revision operation. Please confirm . |  |  | Closed | Parent Product should be in Preliminary state only
8 | Nested Product Governance | General | Promoting a Product to Obsolete state which has sub-prodcuts in release state | Is it allowed? Please explain. OOTB behavior for Logfical Feature-We can promote parent logical feature to obsolete even if its child logical feature is in release state. |  |  | Closed | Jayawant/Arnab to check on EBOM. If it allows, the same behavior to be followed for Nested product. EC allows to move intermediate part in Obsolete state.
9 | Nested Product Governance | page 9-v 2.1 | 3) A warning will be issued if a Product Revision is candidate for deletion, and has a product configuration attached. | 1.As per Ajay,Email notification to be sent to Parent Product Configuration owner about Deletion.Please Confirm whether immediate Parent PC or TOP PC owner. 2. warning message is a pop-up with ok and cancel |  |  | Closed | Rajesh/ Ted to come back on this. Notify both Top PC owner and immediate PC owner.No blocking. From testing perspective QA team will check Icon mails.
10 | Nested Product Governance | page 22 - pdf | <Document the […] Search page which is OOTB. Can pick a different revision… or a different product if desired. > | Please clarify Replace with Higher revision will also allow to replace other product with any available revision. For ex - P1 (B) ¦_P2 (D) If I clickon Replace with Higher rev icon, and then chooser, the search result will display below: P2 - A, B, C, D, E, F P3 - A, B, C P4 - A, B, C 1) If I select P2 -A or B or C or D, it should block the operation with appropriate error message. Please confirm 2) For me, it should not display and allow P3 & P4 to replace as functionality is only for replacing higher revion of same product. It is not a generic Replace with Existing. |  |  | Closed | All lower and higher revisions will be displayed. The command should be renamed to Replace with Higher revision/Product. Ajay to implment cyclic redundancy as mentioned in above query No. 8
| Nested Product Configuration Governance | Version 1.4
11 | Nested Product Configuration Governance | General Roll Down / Roll Up | P1( has CF1 manually added -No roll up from P3) ¦_P2 ¦_P3(has CF1 manually added-No roll down from P1) Scenario: Rollup and Rolldown for same product ---> If we roll down CF1 from P1 to P2 and then roll up CF1 from P3 to the same product P2, what would be the outcome? | Expectation : This should be blocked with appropriate error. Please Confirm. This behavior should be specified in PES. |  |  | Closed | Yes the operation is blocked C3R: Test Case Added
12 | Nested Product Configuration Governance | General Roll Down / Roll Up | Roll Up / Roll Down "Inheritance Type" Column | Whether the column for inherited relationship will also show the information FROM WHERE ( from which product ) the feature was rolled up/down. ( For eg : As a Tooltip when mouse is placed on the rollup/rolled down icon ) To be specified in the PES. For ex - P1( has CF1, CF2) ¦ ¦_P2 ( has CF3, CF1 (rolled down from P1)) ¦ ¦_P3(has CF4, CF1 (rolled down from P1)) How end user will come to know from where CF1 is rolled down? |  |  | Closed | Not in current scope
13 | Nested Product Configuration Governance | General Roll Down / Roll Up | Multiple CFs to be rolled up/ down | Can we select muliple CFs to be rolled down under single/multiple products? PES says on page 24, figure 21 that rollup/rolldown can be done for 1 feature to many products ( 1 to many ) In the same context, will a MANY to MANY relationship supported? Please Confirm. |  |  | Closed | One to many is supported
14 | Nested Product Configuration Governance | Page 11 Template Product | Add Configuration Features to a 'Template Product' | Is 'Template Product' out of scope? If yes, Template Product related information to be removed from the PES. |  |  | Closed | Will be modified in next version of PES. Still there in V1.5
15 | Nested Product Configuration Governance | Page 17--->Create Configuration Feature | 3rd point under figure 13 "If there are no nested Products, show single top node only." | This sentence is invalid. We cannot see nested structure in Configuration features powerview. |  |  | Closed | Will be modified in next version of PES. Still there in V1.5
16 | Nested Product Configuration Governance | Page 19---Design Variant and Configuration Features | Refer Figure 15 and the description above it. | Figure 15 and the description above it appear to be invalid as we always use 'Add Existing' in case of Design Variants. Figure 15 shows the 'Create Configuration Feature Page' which is not relevant. Please confirm. |  |  | Closed | It should be Product Variant not Design Variant. To inform to Ajay.
17 | Nested Product Configuration Governance | Page 21 / Section 3.2.2 --- Add a Product Line | Figure 18 – CF Search Page From Product Lines | If the user does not select a product line on the search page,it should throw a warning to select a product line Expected Warning message. Please confirm |  |  | Closed | User needs to select product line else it won't display results in search window.
18 | Nested Product Configuration Governance | Page 24-25 | Roll Down popup page. | Are we going to have an 'Expand All' and 'Expand n levels' commands on the Roll Down popup page? |  |  | Closed | Ajay to confirm. Under discussion with Ted , will be decided during actual development. Will be added based on Development design.
19 | Nested Product Configuration Governance | Page 26 | Refer Fig 24 | Fig 24 should be changed with approprate parent product's CF powerview. PES to update. |  |  | Closed | Inform to Ajay for update
20 | Nested Product Configuration Governance | Page 28 | Refer Figure 27 | Figure 27 should be changed to remove 'Product Template' from it. PES to update. |  |  | Closed | Changes done. Comment specified in V1.5
21 | Nested Product Configuration Governance | Page 30 | Refer Fig 29 | Fig 29 should be updated as per Note mentioned below it. PES to update. |  |  | Closed | Taken into account in Note.
22 | Nested Product Configuration Governance | Page 31 | Selecting Immediate Parent Products - Rollup from child product | For immediate parent (rollup from child), will the check box always be selected? If so, can we deselect some and keep few? |  |  | Closed | Not a business use case but system will display multiple immediate parents based on the product structure.
23 | Nested Product Configuration Governance | Page 31 | Selecting Template Products section | Selecting Template Products section should be removed. PES update. |  |  | Closed | Will be modified in next version of PES. Still there in V1.5
24 | Nested Product Configuration Governance | Page 32 Section 3.2.5 | Refer Figure 31 - General Query | Will revising a CF replace it in all products with the higher revision of the same automatically? or user needs to do so manually by selecting any higher revision? |  |  | Closed | OOTB tests to be done by Arnab/Jayawant. Fig31 shows Frequency A, B, C are different CFs not revisions
25 | Nested Product Configuration Governance | Page 32 / Section 3.2.5 | Product Effectivity on Feature Options | How to set product effectivity for a Configuration Option? Is it done using inclusion rule between a Configuration Option and a Product? |  |  | Closed | Ted will revert on this.
26 | Nested Product Configuration Governance | Page 34 | Option Effectivity Report | Can we launch the 'Option Effectivity' report for an intermediate level product that has sub-products under it? |  |  | Closed | No, its for Top level Product only
27 | Nested Product Configuration Governance | Pg 37, below fig 36 | Rolled Up Features (Metal Alloy) would not allow the value to be changed. | Which value? Does it Feature option? What if the inherited feature has 3 options under it? Which one would be default selected?) |  |  | Closed | Only selected option from Top Prd structure PC will be shown at Child prd PC creation
28 | Nested Product Configuration Governance | Pg 37, below fig 36 | Point 2 is incomplete.To be updated. | To be updated in PES. |  |  | Closed | This value would be based on" to be deleted & Non Effective Features to be changed to Non Effective Features options
29 | Nested Product Configuration Governance | Acceptance Tests Page 47 | Test Case 2 : Expected result | Assuming 'Actions Menu' is the Global toolbar Actions menu. If yes, Expected result should be changed to--> The New CF should be connected to only the Product Line selected. |  |  | Closed | Expected result should be changed to--> The New CF should be connected to only the Product Line selected.
30 | Nested Product Configuration Governance | Acceptance Tests Page 47 | Test Case 3 | How can we create a configuration feature from a Design Variant? |  |  | Closed | It should be Product Variant not Design Variant. To inform to Ajay.
31 | Nested Product Configuration Governance | Acceptance Tests Page 47 | Test Cases 7 and 8 | Test Cases 7 and 8 are the same. Test case 8 needs to be removed PES to be updated. |  |  | Closed | Tc #8 should be removed
32 | Nested Product Configuration Governance | Acceptance Tests Page 48 | Test Case 11 | 2nd point under the expected result is unclear. |  |  | Closed | Rule Applied with viewing Structure View of Preview BOM of Nested Products. Ajay to update
33 | Nested Product Configuration Governance | Acceptance Tests Page 48 | Test Case 13 | Test Case 13 is related to Product Template. Needs to be removed. |  |  | Closed | Yes . Ajay to update
34 | Nested Product Configuration Governance | Page 20 | Clear Button on Create/Edit Page of Confi Feature for "Product Line" field? | Can we have clear button on Create/Edit Page of Confi Feature for "Product Line" field? |  |  | Closed | Yes, Ajay to update PES
35 | Nested Product Configuration Governance | Page 20 | Add Existing from Product Line Availability? | From where can the user launch this? As per our understanding it should be available:- 1. Product Line-> Configuration Features Powerview-> Actions-> Add Existing from Product Line 2. Model-> Configuration Features Powerview-> Candidate Configuration Feature->Actions-> Add Existing from Product Line 3. Product-> Configuration Features Powerview-> Actions-> Add Existing from Product Line 4. Product Variant-> Configuration Features Powerview-> Actions-> Add Existing from Product Line |  |  | Closed | Only from Product -> Config Features ---
36 | Nested Product Configuration Governance | Page 28 | Parent Product Option | Are we displaying immediate and intermediate Parent Products as well like Roll Down? |  |  | Closed | All Top Products. These are immediate Products from current structure
37 | Nested Product Configuration Governance | Page 28 | Parent Product Option- Refer below structure:- P1 - --P2 ---- - --P3 ---- - ---------P4 (CF1) | As per PES we cannot roll up CF1 from P4 to P2. We can either roll up to P1 or P3. Question:- How can I roll up feature CF1 to P2? Can we roll up or roll down again the rolled up or rolled down feature? |  |  | Closed | 1. From Top Product to roll down 2. Yes
38 | Nested Product Configuration Governance | Page 28 | Parent Product Option- Refer below structure:- P1( Release) - --P2 ---- - --P3 ---- - ---------P4 (CF1) P11( Preliminary) - --P22 ---- - --P33 ---- - ---------P4 (CF1) | Steps:- CF from P4 and Roll Up to Parent Products(P1 and P11) Select Both Question:- Whether Roll Up operation is fully canceled as there is invalid condition. In case of Roll Down, it will not allowed if any invalid condition is selected. (Page No.:-25 "Done" section) |  |  | Closed | Only Preliminary products would be dispalyed in the table for selection
39 | Nested Product Configuration Governance | Adhoc | P1---Structure 1 --P1.1 -----P2 --------P3 CF1, CF2, CF3 --P1.2 -----P4 --------P3 CF1, CF2, CF3 ------P10 P1---Structure 1 ---P2 ------P3 CF1, CF2, CF3 ---P4 ------P3 CF1, CF2, CF3 ------P10 P11---Structure 2 ---P22 ------P3 CF1, CF2, CF3 ---P44 CF11 | Question Immediate Parent option:- I am in P1 Structure1-> If we launch Roll Up on P3 CF1, can I see see only P2 and P4 or can I see P2, P4 and P22(P22 is in Structure 2 which is available in the database) |  |  | Closed | Immediate parents of current context structure Refer extra Use case 1. Rajesh/Ted to come back on this. Refer slide provided by Ted. Summary: In context of Top if same product is used multiple times, immediate parent rollup will be blocked. However, user can use bypass by using add existing rolling up CFs to immediate parents
40 | Nested Product Configuration Governance | Page No 30 | During the Rollup Procedures, the program must do the following.  Notify PC’s that do not have EBOM’s Generated (In this example, PC1, and PC2 only)  Do not Notify PC’s that have an EBOM Generated (In this example, PC3 will not be notified).  Notify PC’s Owner also if the PC is in the Validate state.  Connect the necessary Relationship Marker to indicate the Roll-up has occurred (Configuration Feature Inherited). | Will this behavior valid for Roll Down Operation as well? If yes --to be specified in PES. |  |  | Closed | Same notifications for Roll down operations. Ajay to update PES
41 | Nested Product Configuration Governance | Page No 30 | During the Rollup Procedures, the program must do the following.  Notify PC’s that do not have EBOM’s Generated (In this example, PC1, and PC2 only)  Do not Notify PC’s that have an EBOM Generated (In this example, PC3 will not be notified).  Notify PC’s Owner also if the PC is in the Validate state.  Connect the necessary Relationship Marker to indicate the Roll-up has occurred (Configuration Feature Inherited). | P1 (PC1) ---P2 (PC2) ---P4 ------P3 (PC3) ------P5 (CF1, CF2, CF3) Q1:- When I roll up CF1 from P5 using immediate parent, will the notification goes to PC3 owner or all PC1, PC2 and PC3 owners? Q2:- When I roll up CF1 from P5 using Parent Products Option, will the notification goes to PC1 owner only or all PC1, PC2 and PC3 owners? |  |  | Closed | 1. Only to PC3 owner 2. PC1 owner only
42 | Nested Product Configuration Governance | Page No 32 | Product Effectivity on Feature Options | Not clear on Usability Perspective , as PES doesn’t show from where we are setting Options Effectivity Need updated PES to write test cases for the same. |  |  | Closed | PES to update. QA team will hold off for writing cases as of now
43 | Nested Product Configuration Governance | Page No 35 | Product Effectivity on Products | Can you explain this with simple example.? |  |  | Closed | Clear
44 | Nested Product Configuration Governance | Page No 35 | Product Effectivity on Products | Is the "Inclusion" Rule is available on Top Level Product or for all Nested Sub-Level Products? |  |  | Closed | Available on all products
45 | Nested Product Configuration Governance | Page No 19 | Product.MasterCompositionLibrary | Will there be only one Master Composition Library? Can user set any Product Line as Master Composition Library from UI? |  |  | Closed | 1. Yes 2. No from UI
46 | Nested Product Configuration Governance | Page No 36 | Product Effectivity on Products | 1. Are we displaying only Mandatory Features from Top Parent Product while creating Inclusion Rule? 2. Are we going to display features excluded with effectivity (Mandatory or non-mandatory)in rule creation page?As per our understanding it should not. 3. We need clarification on this screen. A. Only Top Product will be displayed in the context if we try to add rule on Sub-Products? Search icon won't be displayed for selecting another product. B. No exclusion rule can be defined as screenshot talks only about Inclusion? C. What is the significance of keeping "Inclusion" for Top Level Product? |  |  | Closed | 1. Yes,Only Mandatory Features 2. Yes 3A. Yes 3B. Only inclusion rule will be available. 3C. Not displayed
47 | Nested Product Configuration Governance | Adhoc | P1 ¦-CF1 ¦-CO1 ¦-CO2 ¦-LF1 Exclude if CF1-CO1 is selected ¦-LF2 Exclude if CF1-CO1 is selected ¦-LF3 Exclude if CF1-CO1 is selected If we create PC and Check Preview BOM:- It applies inclusion rule and all Logical Features are getting displayed. PC1(Preview BOM Page) ¦-LF1 ¦-LF2 ¦-LF3 | Is is a correct behavior? |  |  | Closed | Jayawant will send scenario to Ted to raise an SR with all details.
48 | Nested Product Configuration Governance | Adhoc - Product Effectivity on Products | P1 (PC1 with CO1 & PC2 with CO2 - CF1, CO1, CO2) ---P2 ------P3 (Inclusion Rule in context of P1 -> Exclude P3 if CO1 is selected) ---P4 ------P10 | 1. Whether Exclusion rule option is available? 2. If yes, when we do Preview BOM for PC1, P3 will be excluded. Please confirm 3. If not, assume the rule on P3 defined as include P3 if CO1 is selected. Now when we do Preview BOM for PC2, P3 will be excluded. Please confirm |  |  | Closed | Only Inclusion rule will be implemented with And & Or operators.
49 | Nested Product Configuration Governance | Roll Up Functionality | P1---Structure 1 ---P2 ------P3 CF1, CF2, CF3 P11---Structure 2 ---P22 ------P3 CF1, CF2, CF3 P111---Structure 3 ---P222 ------P3 CF1, CF2, CF3 | Roll Up CF1 in context of P1-> Selecting Parent Product Option:- 1. We can see P1, P11 and P111 2. Roll Up to P1 only Roll Up CF1 in context of P1-> Selecting Parent Product Option:- 1. We can see P1, P11 and P111 Can we see P1 Again as we have rolled up CF1 already 2. If yes, when P1 is in selection of Rolling Up--> it should throw an error |  |  | Closed | Exclude the already rolled up Parents from list
50 | Nested Product Configuration Governance | Adhoc | Edit Details Page Configuration Feature | Whether Product Line field is editable on Edit Details Page of CF? |  |  | Closed | Yes, should allow Edit Product Line field
51 | Nested Product Configuration Governance | Adhoc Page No 35 | Product Effectivity on Products | Are we adding one more column Rule Expression? Which will help user to see exact rule applied against respective product. |  |  | Closed | Open SCR as future enhancement
52 | Nested Product Configuration Governance | Page No 33 | Product Effectivity on Feature Options | 1. How are we setting the Product Effectivity on Feature Options? 2. How to define input parmeters (UI capability) is not mentioned in PES. |  |  | Closed | The command will be available from Top Product & Sub Products having sub child product below it > Conf Features> Actions menu ONLY
53 | Nested Product Configuration Governance | Page No 33 | Product Effectivity on Feature Options | 1. What would be the command name under Actions menu of Top Product? 2. Only the Nested Products which has the same Feature with Option from Top to Bottom would be displayed in the search window please confirm? 3. On selecting few of the Product From the Search window, will it auto refresh the Configurations Feature Powerview updating latest results under column Options Effectivity "Limited to Product" |  |  | Pending | 1. Set Feature Options effectivity 2. Yes 3. It should Ted to update Fig 32
54 | Nested Product Configuration Governance | Page No 33 | Product Effectivity on Feature Options There will be a limit to the number of items (products) that could be displayed (maximum of five). After this limit, a “…” would indicate more effectivity have been set but not shown. The user would have to drill deep to find the details. | For more than 5 Products in the list, how user can check list of Products? Will "…" behave as hyperlink and new window will be displayed with list of all products? Please clarify. |  |  | Pending | Ajay/Ted/Rajesh to come back on this
55 | Nested Product Configuration Governance | Page No 33 | Product Effectivity on Feature Options There will be a limit to the number of items (products) that could be displayed (maximum of five). After this limit, a “…” would indicate more effectivity have been set but not shown. The user would have to drill deep to find the details. | How can user remove the selected product from the list of earlier selection made? |  |  | Pending | Ajay/Ted/Rajesh to come back on this
56 | Nested Product Configuration Governance | Page No 33 Figure 32 – Feature Effectivity Summary | Product Effectivity on Feature Options Question based on Figure 32 – Feature Effectivity Summary | What are the different ways to define Product Effectivity on Feature Options? 1. Is it only from Product Line> Configuration Features> Under Options Effectivity> Limited to Product Column and How? 2. If it is a chooser against each option under Limited to Product Column , which all products are selectable in the search window? Is it only Top Products of all models? |  |  | Closed | Answered above
57 | Nested Product Configuration Governance | Page No 33 Figure 32 – Feature Effectivity Summary | Product Effectivity on Feature Options Question based on Figure 32 – Feature Effectivity Summary | Can we define Product Effectivity on Feature Option from Top Product > Configuration Features> Under Options Effectivity> Limited to Product Column and How? 2. If it is a chooser against each option under Limited to Product Column , which all products are selectable in the search window? Is it only Sub Products of Top Product? |  |  | Closed | Answered above
58 | Nested Product Configuration Governance | Page no 38 | Feature Effectivity on Feature Options | What are the different ways to define Feature Effectivity on Feature Options? 1. Is it only from Top Product > Configuration Features> Under Options Effectivity> Limited by Feature Column and how? 2. Effectivity is defined only by rules or is there any other way? Are we modifying inclusion OOTB Define rule page? If yes is it applicable from all the pages? (Product Line/Model/Product Variant) 3. As we are restricting to define rule only on Non-Mandatory Feature, so can't we define rule on Mandatory Feature and Options (OOTB) as well as non-mandatory feature options (OOTB) |  |  | Closed | 1. We can define on features and not on options. It is only for Optional Configuration features (Non-Mand - May select) Ted: The options that the rules based on can come from Mandatory features 2. New column with Inclusion link will be provided for Feature Eff on Feature Options 3. As we are providing new command this query is not valid. OOTB capability of defining rules still persist.
59 | Nested Product Configuration Governance | Page no 38 | Feature Effectivity on Feature Options | Are we defining rule on Configuration Option or Configuration Feature? Because if we define exclusion rule on Configuration Option, option will get excluded and not the Configuration Feature. |  |  | Closed | On Configuration Feature and not on option. Only Inclusion rule can be applied
60 | Nested Product Configuration Governance | Page no 38 | Setting Effectivity Rules  Exclusion Only  Features Selected can only be Mandatory Features  Simple Rules (And and OR) like Product Effectivty | Features Selected can only be Mandatory Features Do you mean to say, defining exclusion rule in front of Mandatory Feature or while defining exclusion rule we can only select Mandatory Feature from the Create Exclusion Rule dialog |  |  | Closed | Only Mandatory features will be displayed in the Rule creation dialog and user can select respective option
61 | Nested Product Configuration Governance | Page no 39 | A simple Inclusion rule will be provided, for setting Feature effectivity. | Are we going to provide Both Exclusion and Inclusion OR only exclusion OR Only Inclusion. Please confirm |  |  | Closed | Inclusion - limited to 5 options only ( 4 Operators) Ted to update PES Rajesh Need to Update Test Case with no restrictions for Operatos
62 | Nested Product Configuration Governance | Page no 38 and 39 | Screenshots on Page 38 and 39 | Screenshots on Page 38 and 39 should be updated 1. Page 38- a. Screenshot should be of Top Parent Product-> Configuration Features Powerview b. Limited by Feature column value should be displayed for Feature only and not against Option 2. Page 39- a. If the rule is set for Color Configuration Feature, this Feature with option should not be displayed in Rule Define Screen b. Only mandatory feature with options should be displayed for Selection c. If we are allowing inclusion-exclusion both, drop down arrow should be displayed for Comparision Operator section |  |  | Pending | Yes, Ted to update
63 | Nested Product Configuration Governance | Adhoc | Product Structure:- P1 CF1 ¦--P2 CF1 (Rolled Down from P1) P1 ¦-CF1------Exclude CF1 if CF2::CO3 is selected ¦--CO1 ¦--CO2 ¦-CF2------Exclude CF2 if CF3::CO5 is selected ¦--CO3 ¦--CO4 ¦-CF3 ¦--CO5 ¦--CO6 P2 ¦-CF1--- Rolled Down from P1 ¦--CO1 ¦--CO2 ¦-CF4 ¦--CO7 ¦--CO8 Steps: 1. create PC1 for P1 with selections as CF3- CO5 2. PC Creation window will be:- P1 ¦-CF1------This Feature will not get excluded as CF2 is greyed out and un-selectable ¦--CO1 ¦--CO2 ¦-CF2------Excluded by effectivity(Greyed Out) ¦--CO3 ¦--CO4 ¦-CF3 ¦--CO5 (Selection made) ¦--CO6 3. Create Nested PC2 for P2 in the context of PC1 4. Create PC will be :- P2 ¦-CF1--- User will be allowed to make selections ¦--CO1 ¦--CO2 ¦-CF4 ¦--CO7 ¦--CO8 | Note:- In case if we can define effectivity on both mandatory and non-mandatory feature:- Question:- What the Action column will display in both Edit Options Pages of PC1 and PC2? |  |  | Closed | In valid scenario, as we can defined Feature Options effectivity for Non-Mand feature
64 | Nested Product Configuration Governance | Adhoc | Rolled Up or Rolled Down Feature | Can we make Rolled Up or Rolled Down Feature Mandatory to Non-Mandatory from its original product context and also from the Products context where this feature is rolled up or Rolled Down. |  |  | Pending | Not allowed. Note: To add trigger on relationship. Ted to update Nest Prod Conf Gov PES.
65 | Nested Product Configuration Governance | Adhoc | Making Configuration Feature from Mandatory to Non-Mandatory which is being used in the Rule Expression for Feature Effectivity on Feature Options | P1 ¦--P2 ¦--P3 P1 ¦--CF1 (NM) ----------- Include if CF3::CF3 CO1 is selected ¦--CF1 CO1 ¦--CF1 CO2 ¦--CF2 (NM) ----------- Include if CF3::CF3 CO1 is selected ¦--CF2 CO1 ¦--CF2 CO2 ¦--CF3 (M) ¦--CF3 CO1 ¦--CF3 CO2 1. Can we change the Mandatory CF3 as Non-Mandatory? 2. Can we change the Non-Mandatory CF1 as Mandatory? |  |  | Pending | Not allowed. Note: To add trigger on relationship. Ted to update Nest Prod Conf Gov PES.
66 | Nested Product Configuration Governance | Ad-Hoc | Replace with Products | on Replace with Product-what will happened to Mandatory features/roll down features of product to be replace | Open |  | Pending | When we are replacing the Product with higher revision of same Product, by default it carries forward Conf And Log Feature with it. Also if the Product which we are replacing has some Configuration Features as Rolled Up or Rolled Down, it will carry forward the Icons for Rolled Up and Rolled Down Feature for new revision. When we are replacing the Product with some other Product, we should be able to see only Configuration and Logical Features of Newly Replaced Product As per Ajay, need to Revisit for this behavior
67 | Nested Product Configuration Governance | Adhoc | P1 (CF1, CF2) ¦--P2 ¦--P3 A (CF1--Rolled Down from P1, CF4--Rolled Up from P4), CF6 ¦--P4 (CF4) P3 B ¦--CF1--Rolled Down from P1 ¦--CF4--Rolled Up from P4 ¦--CF5 Newly Created from P3 B's Context | When I Replace P3 A with P3 B, P1 (CF1, CF2) ¦--P2 ¦--P3 B (CF1--Rolled Down from P1, CF4--Rolled Up from P4, CF5 Newly Created from P3 B's Context) ¦--P4 (CF4) Q1. Will it also retains the Rolled Up Icon for CF4 or Rolled Down icon for CF1 under Inheritance Type Column? Q2. So in P3 A-> Configuration Features, whether Rolled Up Icon for CF4 or Rolled Down icon for CF1 will still be available under Inheritance Type Column? |  |  | Closed | 1. Yes Inheritance type icon for Roll up & down will eb dispalyed. 2.P3-A will not show Inheritance type icons
68 | Nested Product Configuration Governance | Adhoc | P1 (CF1, CF2), PC1-P1 ¦--P2 ¦--P3 A (CF1--Rolled Down from P1, CF4--Rolled Up from P4), PC3-P3A ¦--P4 (CF4) P3 B ¦--CF1--Rolled Down from P1 ¦--CF4--Rolled Up from P4 ¦--CF5 Newly Created from P3 B's Context | When I Replace P3 A with P3 B, P1 (CF1, CF2), PC1-P1 ¦--P2 ¦--P3 B (CF1--Rolled Down from P1, CF4--Rolled Up from P4, CF5 Newly Created from P3 B's Context), PC3-P3B ¦--P4 (CF4) If I open PC3-P3A Separately from P3 A's context-> Select Edit Options:- Q1. Will it allow user to select another option for CF1 which is rolled down from P1? Q2. What will be the value under Action column for CF1? (Will it be Mandatory Selected or Mandatory?) |  |  | Closed | 1. Will work as OOTB 2. It should be Mandatory
69 | Nested Product Configuration Governance | Adhoc | Continue from above steps | Now if I Replace P3 B with P3 A again, P1 (CF1, CF2), PC1-P1 ¦--P2 ¦--P3 A (CF1--Rolled Down from P1, CF4--Rolled Up from P4), PC3-P3A ¦--P4 (CF4) Q1.In the Nested Preview BOM of PC1-P1-> Will it show PC3-P3A in front of P3A? Q2. If yes, when I do Edit Options of PC3-P3 A-> Will it show Mandatory Selected under Action Column for CF1 with only one non-selectable option available? Q3. Assuming PC3-P3A is edited by selecting another option from CF1 when it got replaced initially, so now what will be displayed in the Edit Options Page of PC3-P3A if Q1 is true? Q4. What will happen to PC3-P3B and rolled up/Rolled Down feature icon of CF1 in the context of P3 B? |  |  | Pending | 1. It will not show PC3-P3A. It will be removed once Top Product & P3A are released. 2. In valid as Q1 is not true. 3. Invalid as Q1 is not true. 4. Inheritance type icon will not be shown. PC3-P3B will work as OOTB. Will be done at the end of Development. Ajay will update the PES.
70 | Nested Product Configuration Governance | Adhoc | Removing the Sub-Product From where Configuration Feature is rolled up | Q1. What will be displayed under Inheritance Type column of Top Product-> Configuration Feature(Rolled Up), Will it show or not show the Rolled Up icon? Q2. If I open Sub-Product from outside and then Open PC created for this sub-product in the Top Parent Product Context, what will be the Action Column value for the Rolled Up Feature? |  |  | Closed | 1. Icon will disappear (removed) 2. Behave as OOTB.
71 | Nested Product Configuration Governance | Adhoc | Deleting the Sub-Product From where Configuration Feature is rolled up | What will be displayed under Inheritance Type column of Top Product-> Configuration Feature(Rolled Up), Will it show or not show the Rolled Up icon? |  |  | Closed | 1. Icon will disappear (removed) 2. Behave as OOTB.
72 | Nested Product Configuration Governance | Adhoc | Deleting the Top Product From where Configuration Feature is rolled down | What will be displayed under Inheritance Type column of Sub Product-> Configuration Feature(Rolled Down), Will it show or not show the Rolled Down icon? |  |  | Closed | 1. Icon will disappear (removed) PC can be edited with user selected options for rolled down features at Sub product PC level.
73 | Nested Product Configuration Governance | Adhoc | P1 (CF1) (CF2 --Rolled Up from P6) ¦-P2 ¦-P3 (CF1 -- Rolled Down from P1) ¦-P4 ¦-P5 (CF2 --Rolled Up from P6) ¦-P6 (CF2 -- Mandatory Feature) ¦-P7 (CF1 -- Rolled Down from P1) | Q1. Can we Cancel Rolled Up or Rolled Down Configuration feature from Source and Target Products both? OR Only from Target Product? OR Only from Source Product? |  |  | Closed | Currently we will go with providing ability from Source and Target Products. The relationship & inheritance type status icon of roll up & roll down will be removed. **To raise enhancement issue on cancel roll up & roll down behavior for providing intermediate dialog showing list of products for user to select.
74 | Nested Product Configuration Governance | Adhoc | In continuation to the above query (query 73)… | Q1. Will Cancel Rolled Up or Rolled Down Operation remove the Rolled Up or Rolled Down Feature from Target Product? OR Only Relationships and Icons under Inheritance Type Column will be disconnected and that Feature Still remains connected to Target Product without Rolled Down or Rolled Up Relationship with Source Product |  |  | Closed | Only Relationships and Icons under Inheritance Type Column will be disconnected and that Feature Still remains connected to Target Product without Rolled Down or Rolled Up Relationship with Source Product
75 | Nested Product Configuration Governance | Adhoc | In continuation to the above query (query 73 & 74)… | After Cancel Rolled Up or Rolled Down Operation can we toggle Mandatory feature which was Rolled Down or Rolled Up from Target and Source Product? |  |  | Closed | Yes
76 | Nested Product Configuration Governance | Product Effectivity on Feature Options | P1 (Color) ¦-P2 (Color- Manually Added) ¦P3 (Color- Rolled Down from P1), Frequency-Manually Added Color ¦-Red ¦-Green ¦-White Frequency ¦-30 ¦-50 1. Options Effectivity Set on P3 for Options Red and Green Only 2. Create Top PC for P1 selecting Color option as White 3. Now in the Context of Top PC-> Create Nested PC-1 for Product P3 4. Check Create Product Configuration Page for Options Selection | As per Product Effectivity on Feature Options set on Product P3, Option White will not be displayed in Options Selection Page of PC and as per Nested Product PC behavior white option will remain Mandatory Selected for Sub-Products PC. Q1. What will be the Option Selection for Color Feature when user create PC for P3 in the context of Top PC? According to us, Color Feature should be displayed as greyed out without any option, also Action column should show another status than Mandatory Selected. What would be the Status value? |  |  | Pending | Will revisit when Ajay works on PC creation page Only Rolled Down should be blocked
77 | Nested Product Configuration Governance | Roll Up/Roll Down/Design Variant | Refer Ajay's mail: Dated Oct 16 Use Case: If we create a Design Variant for a logical feature by selecting a CF. Then the CF gets Rolled up to Product and the selected CF gets connected to Product with Varies By Relationship. And if the CF is already present on the Product then the CF relationship(whether it is Configuration Features or Mandatory Configuration Features) is set to Varies by using setType() API and set the attribute Rolled Up as true. And on removal of design Variant the connection type is reset using value of Configuration Type Attribute(Mandatory, Configuration, System). In our case, if we have a Mandatory Configuration Feature(MCF) which is rolled down to a number of products. Then on adding a design variant using the same MCF the relationship will be replaced with Varies by and the Rolled up/down information will be lost. Possible Solution for this, is to remove the CFs which are being used as rolled up rolled Down from Full search while adding CFs from Product Line as Design Variant. Please consider this use case and let us know the possible solution for this. | Q1. In case a Mandatory Configuration Feature(MCF) which is rolled down to a number of products from Top Product, while adding a design variant selecting same MCF from Product line to the Product on which MCF is rolled down, will the user be able to add the same or will it restrict ? |  |  | Closed | As per discussion with Ajay, in current implementation we are going to restrict the user to add same Rolled Down Feature from Product Line as a Design Variant In future the behavior would be changed as below:- While adding the MCF, a warning message will appear saying "Rolled Up/Rolled Down relationship will be removed. Do you want to continue Yes or Cancel?" QA Team will raise SCR for this future enhancement and would be part of Good to have list
78 | Nested Product Configuration Governance | Roll Up/Roll Down/Design Variant | P1 ¦-P2 ¦-P3 ¦-P4 P1 ¦-CF1 P4 ¦-CF4 | Q1. What wll be the new behavior if we Roll Down CF1 from P1 to P4? Q2. What wll be the new behavior if we Roll Up CF4 from P4 to P1? Q3. Will both the Roll Up and Roll Down icon available if we perform either of the operation? |  |  | Closed | Yes
79 | Nested Product Configuration Governance | Roll Up/Roll Down/Design Variant | P1 ¦-P2 ¦-P3 ¦-P4 P1 ¦-CF1 Q.1 1. Roll Down CF1 from P1 to P4 2. Cancel Roll Down either from P1 or P4 context 3. Again Roll Down CF1 from P1 to P4 P4 ¦-CF4 Q.2 1. Roll Up CF4 from P4 to P1 2. Cancel Roll Up either from P1 or P4 context 3. Again Roll Up CF4 from P4 to P1 | Q1. Can we Roll Down Feature CF1 from P1 to P4 even if, it is already available under P4 Q2. Can we Roll Up Feature CF4 from P4 to P1 even if, it is already available under P1 |  |  | Closed | Yes
80 | Nested Product Configuration Governance | Roll Up/Roll Down/Design Variant | P1 ¦-P2 ¦-P3 ¦-P4 P1 ¦-CF1 1. Roll Down CF1 from P1 to P4 | Q1. Once we Roll Down CF1 from P1 to P4, it wll be available under P2 and P4 as well. But these wll be hidden. So if we make CF1 'Make Visible', will it be Mandatory or Non-Mandatory Feature? |  |  | Closed | Yes

## Future Enhancement
Sr No | Functionality | Functionality Details | Comments
1 | Product Effectivity on Products | Are we adding one more column Rule Expression? Which will help user to see exact rule applied against respective product. | Open SCR as future enhancement
2 | Add to Classification | Do we have any way to traverse to all the Products in the database? Currently we can only traverse to Product Lines and Models from My Desk | Open SCR as future enhancement
3 | Add to Classification | If RMB allows us the 'Add to Classification' on the Product Lines Navigator page, can we have the same functionality on the Models Navigator page too to enhance usability (The Actions button on the Models Navigator page has all commands related to Products so we are going to be dealing with products on this page. It makes more sense to have the 'RMB' Actions on this page more) | Open SCR as future enhancement