## FS Queries
Sr No | Document | Page / Section | Reference | Inquiry | Category | Requestor | Comments / Response | Responder
1 | NA | NA | NA | Understanding on which environment will be running our testcases. |  |  | Short term - m10, longer term - depending on functionality. For example if tests are aiming at testing FD14 - it should be environemnt that targets it. Check with CI/CD team on having local environments | Kyrylo Mytrofanov
2 | Test Automation | Slide 8 | Point 1 | What are team green, purple, orange teams mentioned in the ppt |  |  | Names of Scrum teams in JLR | Kyrylo Mytrofanov
3 | NA | NA | NA | Regarding Project Timeline can you brief the team, how the project is going to proceed in steps?
4 | NA | NA | NA | Which is the IDE (integrated development environment) we are going to use? |  |  | We recommend using Eclipse with Pydev. Kyrylo will upload zipped eclipse and python distributable | Kyrylo Mytrofanov
5 | NA | NA | NA | Which Native apps and Web apps are going to be used in the project? |  |  | Kyrylo can't answer, check with CI/CD team. For native apps - thick client, catia, delmia, simulia | Kyrylo Mytrofanov
6 | NA | NA | NA | Will the test data be already present or we have to create it? |  |  | If you can - create data before test execution, and cleanup afterwards. If data requirements are too complex - assume its already there. Check with CI/CD team on how data is going to be managed | Kyrylo Mytrofanov
7 | Test Automation | Slide 9 | Point 2,3 | What will be the duration of each sprint? Is there any exit criteria applicable? |  |  | 2 weeks long. Confirm with Rob Williams any other details regarding sprints | Kyrylo Mytrofanov
8 | NA | NA | NA | What will be the bandwidth of application engineer available for QA team? |  |  | As much as needed, if not enough - escalate and we'll improved bandwidth | Kyrylo Mytrofanov
9 | NA | NA | NA | For what purpose we are going to use selenium? |  |  | For web GUI interaction | Kyrylo Mytrofanov
10 | NA | NA | NA | Can we use KanBan for tracking issues |  |  | Sprint backlog (which is kanban-like), get more information from Rob Williams | Kyrylo Mytrofanov
11 | NA | NA | NA | Is native apps installation required on JLR laptops i.e our machines? OR how can we execute the scripts for native apps(on remote computer where native apps is already installed) |  |  | Runner already has native apps installed, current JLR laptops at 3DGS are not specced for native apps | Kyrylo Mytrofanov
12 | NA | NA | NA | Which IDE Kyrylo is using OR can you recommend any IDE? |  |  | Answered above
13 | NA | NA | NA | How 12 scrum teams will work with 3DGS team? What will be the resource allocation and mapping. |  |  | Confirm with Rob Williams | Kyrylo Mytrofanov
14 | NA | NA | NA | Where will we commit our scripts in git repository? |  |  | In the main repository, using the existing repo structure, committed via merge requests | Kyrylo Mytrofanov
15 | NA | NA | NA | In GIT lab when we refer the repository, Under Commits what are Green, Wizz-native-apps,merge branch. For ex: Green-703 #comment: fix create task issue |  |  | Those are commit messages, they are describing the nature of the code change. For branch names - use naming convention (to be described later)# | Kyrylo Mytrofanov
16 | NA | NA | NA | In GIT lab when we refer the repository, Under Branches what are Active, Stale branches? |  |  | Gitlab labels unused branches as Stale and hides them from main view
17 | NA | NA | NA | When will we get access to the runner2 |  |  | Target - middle next week (week of 22nd). For now - use runner one, but lets discuss this in more details | Kyrylo Mytrofanov
18 | NA | NA | NA | How will we differentiate between the native apps in the repository |  |  | Native app tests should go into the same repository, but for reusable helper methods still separate them between native_app_helper_methods and selenium_helper_methods | Kyrylo Mytrofanov
19 | NA | NA | NA | Where will we do our first dry run?(before doing commit into the Git) |  |  | Once we have code ready to be merged into main branch. To be discussed on 19th regarding first tasks | Kyrylo Mytrofanov
20 | Test Automation | slide 2,3,4 | NA | What is "Extraction Script" in the Test Automation cycle workflow? |  |  | Don’t worry about it, its out of your scope | Kyrylo Mytrofanov
21 | Test Automation | slide 2,3,4 | NA | What is Backlog refining in the Test Automation cycle workflow? |  |  | Don’t worry about it, its out of your scope | Kyrylo Mytrofanov
22 | Test Automation | slide 2 | NA | What does Iterate on feature file mean in Test Automation cycle? |  |  | Continuous two-way process of improving feature file to be more test automation-friendly | Kyrylo Mytrofanov
23 | it_structure | slide2 | NA | Will there be any intergration between scrum teams or different modules on Dev Env2(Shared)? |  |  | Mostly by either working on the same environemnt or working on the same codebase | Kyrylo Mytrofanov
24 | NA | NA | NA | Are jump server and runner the same. |  |  | Kyrylo needs to check with Chad what jump server is | Kyrylo Mytrofanov
25 | NA | NA | NA | What do we do in CI / CD - Pipelines and Jobs. Can you please re-explain |  |  | Pipelines are made of jobs (individual bubbles), that are steps of the execution | Kyrylo Mytrofanov
26 | NA | NA | NA | By when we will be getting the JLR laptops for other team members. |  |  | Kyrylo can't answer, check with Chad Esler. | Kyrylo Mytrofanov